## ProjectSchedule
GETINSYNC NEXTGEN - Q1 2026 MASTER PLAN v2.0 | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
GetInSync Strategic Management |  | Project Start: | 2026-02-10
Stuart Holtby |  | Today: | 2026-02-14
|  | Display Week: | 1 |  |  | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
 | time axis 2026-02-09 to 2026-04-05
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-02-09 to 2026-04-05
ARCHITECTURE SPRINT (COMPLETE) | Stuart | 100% | 2026-02-10 | 2026-02-14 | 5
Visual Tab architecture v1.0 | Stuart | 100% | 2026-02-10 | 2026-02-10 | 1
Technology Stack ERD v1.0 + Addendum v1.1 | Stuart | 100% | 2026-02-10 | 2026-02-11 | 2
Technology Health Dashboard arch v1.0 | Stuart | 100% | 2026-02-12 | 2026-02-13 | 2
Risk Boundary ADR + Cost Model Addendum | Stuart | 100% | 2026-02-13 | 2026-02-13 | 1
Infrastructure Boundary Rubric v1.0 | Stuart | 100% | 2026-02-14 | 2026-02-14 | 1
Lifecycle Intelligence v1.0 → v1.1 | Stuart | 100% | 2026-02-14 | 2026-02-14 | 1
Gamification architecture v1.2 | Stuart | 100% | 2026-02-14 | 2026-02-14 | 1
Marketing Explainer v1.6 → v1.7 | Stuart | 100% | 2026-02-13 | 2026-02-14 | 2
Manifest v1.18→v1.23 + Changelog | Stuart | 100% | 2026-02-10 | 2026-02-14 | 5
COMPLETED (PRE-SPRINT) | Team | 100% | 2026-02-07 | 2026-02-13 | 7
Phase 25.9-25.10 (RLS + Schema) | Stuart | 100% | 2026-02-07 | 2026-02-08 | 2
Phase 28: Integration Management | Stuart + AG | 100% | 2026-02-07 | 2026-02-08 | 2
SOC2 Audit Logging Infrastructure | Stuart | 100% | 2026-02-09 | 2026-02-09 | 1
Google OAuth verified & live | Stuart | 100% | 2026-02-12 | 2026-02-12 | 1
Nested Portfolio UI | AG | 100% | 2026-02-13 | 2026-02-13 | 1
Audit log backfill + schema backup | Stuart | 100% | 2026-02-13 | 2026-02-13 | 1
FOUNDATION CATCHUP | Stuart + AG | 0% | 2026-02-17 | 2026-02-21 | 5
Power BI views deployment (14 views) | Stuart | 0% | 2026-02-17 | 2026-02-17 | 1
First Power BI dashboard | Stuart | 0% | 2026-02-18 | 2026-02-18 | 1
Delta training — Namespace UI | Stuart + Delta | 0% | 2026-02-18 | 2026-02-18 | 1
Delta training — Garland workflow | Stuart + Delta | 0% | 2026-02-19 | 2026-02-19 | 1
Enable Dependabot + SSO decision | Stuart | 0% | 2026-02-17 | 2026-02-17 | 1
Phase 28 bug fixes (13 items) | AG | 0% | 2026-02-17 | 2026-02-19 | 3
Namespace UI polish (slug, region) | AG | 0% | 2026-02-20 | 2026-02-20 | 1
Website update | AG + Delta | 0% | 2026-02-20 | 2026-02-21 | 2
TECHNOLOGY HEALTH DASHBOARD | Stuart + AG | 0% | 2026-02-24 | 2026-03-07 | 12
Schema — applications columns | Stuart | 0% | 2026-02-24 | 2026-02-24 | 1
Schema — DP + tech product columns | Stuart | 0% | 2026-02-24 | 2026-02-24 | 1
RLS + GRANTs + audit triggers | Stuart | 0% | 2026-02-24 | 2026-02-24 | 1
Lifecycle reference data seeding | Stuart | 0% | 2026-02-25 | 2026-02-25 | 1
Database views (4 new views) | Stuart | 0% | 2026-02-25 | 2026-02-26 | 2
Lifecycle badge on DP tech tagging | Stuart | 0% | 2026-02-26 | 2026-02-27 | 2
Riverside demo data — tech tagging | Stuart | 0% | 2026-02-27 | 2026-02-28 | 2
Crown Jewel flags on key apps | Stuart | 0% | 2026-02-28 | 2026-02-28 | 1
Garland import (363 apps) | Stuart + Delta | 0% | 2026-02-26 | 2026-02-28 | 3
Dashboard UI — KPIs + lifecycle | AG | 0% | 2026-03-03 | 2026-03-03 | 1
Dashboard UI — workspace breakdown | AG | 0% | 2026-03-04 | 2026-03-04 | 1
Dashboard UI — infra report | AG | 0% | 2026-03-04 | 2026-03-05 | 2
Dashboard UI — blast radius view | AG | 0% | 2026-03-05 | 2026-03-06 | 2
Testing + validation | Stuart + Delta | 0% | 2026-03-06 | 2026-03-07 | 2
IT VALUE CREATION | Stuart + AG | 0% | 2026-03-05 | 2026-03-14 | 10
Schema — initiatives table | Stuart | 0% | 2026-03-05 | 2026-03-05 | 1
Schema — findings table | Stuart | 0% | 2026-03-05 | 2026-03-05 | 1
Schema — junctions + RLS + audit | Stuart | 0% | 2026-03-06 | 2026-03-06 | 1
Auto-generate lifecycle findings | Stuart | 0% | 2026-03-06 | 2026-03-07 | 2
UI — Findings list view | AG | 0% | 2026-03-10 | 2026-03-10 | 1
UI — Initiatives list + detail | AG | 0% | 2026-03-10 | 2026-03-11 | 2
UI — Kanban board view | AG | 0% | 2026-03-11 | 2026-03-12 | 2
UI — Roadmap timeline view | AG | 0% | 2026-03-12 | 2026-03-13 | 2
UI — Value dashboard | AG | 0% | 2026-03-13 | 2026-03-13 | 1
Testing + demo data | Stuart + Delta | 0% | 2026-03-13 | 2026-03-14 | 2
POLISH + PREP | Stuart + AG | 0% | 2026-03-17 | 2026-03-31 | 15
UI consistency pass | AG | 0% | 2026-03-17 | 2026-03-19 | 3
Power BI Garland demo | Stuart | 0% | 2026-03-19 | 2026-03-20 | 2
Demo script development | Stuart | 0% | 2026-03-20 | 2026-03-20 | 1
Website content update | Stuart + Delta | 0% | 2026-03-23 | 2026-03-24 | 2
Integration Mgmt remaining fixes | AG | 0% | 2026-03-24 | 2026-03-25 | 2
Documentation pass | Stuart + Delta | 0% | 2026-03-26 | 2026-03-27 | 2
Q1 review + Q2 planning | Stuart | 0% | 2026-03-30 | 2026-03-31 | 2
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.